## Sprint Product Backlog
SPRINT PRODUCT BACKLOG Enter data below, chart will populate automatically
User story ID | Backlog Item | Status | Original Estimate | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Sprint Review
| User Authentication |  | 35 | Week3: 13; Week4: 22
7 | Register membership | Done | 10 | Week3: 3; Week4: 7
15 | Login as a member | Done | 5 | Week3: 2; Week4: 3
8 | Register Mentor | Done | 10 | Week3: 4; Week4: 6
16 | Login as a mentor | Done | 5 | Week3: 2; Week4: 3
17 | Login as an admin | Done | 5 | Week3: 2; Week4: 3
| Booking Service |  | 25 | Week4: 15; Week5: 10
5 | Booking Mentor Program | Doing | 10 | Week4: 5; Week5: 5
6 | Space Booking | Doing | 5 | Week4: 5
10 | Request for room assessing | Doing | 10 | Week4: 5
| Information Present |  | 20
1 | Event info | NTD | 5
2 | Funding info | NTD | 5
3 | QUT Foundry info | NTD | 5
4 | Mentorship info | NTD | 5
| Mentor Admin Mgmt |  | 25
9 | Mentor Program Booking Request | NTD | 10
20 | Add Mentor Program | NTD | 5
21 | Remove Mentor Program | NTD | 5
22 | View Timetable | NTD | 5
| Entreprenuer Administer Management |  | 15
23 | Cancel Mentor Program | NTD | 10
24 | View Timetable | NTD | 5
| Foundry Admin Mgmt |  | 20
18 | Manage membership request | NTD | 10
19 | Foundry admin Mgmt | NTD | 10
| Edit Website Content |  | 25
14 | Content editing | NTD | 25
| Community |  | 15
11 | Sharing idea | NTD | 5
12 | communication | NTD | 5
13 | Matchup People | NTD | 5
| Weekly Achivement |  | 180 | Week2: 0; Week3: 13; Week4: 37; Week5: 5
|  |  | Estimate (p/w) | 0 | 18 | 36 | 54 | 72 | 90 | 108 | 126 | 144 | 162 | 180
|  |  | Achived (Total) | Week2: 0; Week3: 13; Week4: 50; Week5: 55